AROGYA LINK

Implementation Documentation — SIH 2026

# 04 — Phases.md | Implementation Phases

Purpose: Break implementation into buildable phases. The supplied plan defines Phases 0–14 and an addendum with Phases 15–19; the dependency-aware order below preserves those capabilities while grouping the addendum according to its stated dependencies.

| Phase | Name | Main Work | Definition of Done |
| --- | --- | --- | --- |
| 0 | Project Foundation | React/Vite patient + doctor apps, FastAPI app factory, PostgreSQL, SQLAlchemy, Alembic, Pydantic, CORS, health endpoint. | Both frontends communicate with FastAPI and database health is verified. |
| 1 | Supabase Authentication | Supabase Auth, supabase-js, protected dashboard routes, token verification in FastAPI. | Doctor/Admin can sign in and access protected routes. |
| 2 | Staff Roles & Authorization | staff_profiles, require_doctor/require_admin and backend endpoint checks. | Signed-in users cannot perform actions outside their role. |
| 3 | Patient Session & Consent | patients, encounters, consent; /session, /consent and encounter validation. | Every intake action is linked to a valid consented encounter. |
| 4 | Adaptive Clinical Intake | questions.json, question_engine.py, adaptive React UI, answers table. | Touch-only intake completes without AI or voice. |
| 5 | Deterministic Red-Flag Engine | red_flags.json, Python evaluator, evidence-backed red_flags table. | Same input produces the same safety result. |
| 6 | Doctor Dashboard | Queue, patient detail, review/edit/approve workflow. | Doctor can review deterministic workflow before AI. |
| 7 | Real-Time Escalation | FastAPI WebSockets, EscalationManager, escalations table. | Critical input creates persistent escalation and live alert. |
| 8 | Document Upload & OCR | Upload validation, document metadata, PaddleOCR, OCR status. | OCR works independently before Gemini. |
| 9 | Voice Input | Audio capture, Bhashini/AI4Bharat primary STT, Whisper fallback, transcript confirmation. | Voice failure does not block intake. |
| 10 | Gemini Clinical Summary | llm_service.py, structured Gemini response, Pydantic validation, versioned summaries. | Doctor receives a validated Gemini draft. |
| 11 | Contradiction Detection | Deterministic field comparisons and contradictions table. | Conflicts are surfaced for doctor review, not auto-resolved. |
| 12 | Audit Logging | Append-only audit_log and log_action helper. | Sensitive actions are traceable to authenticated staff. |
| 13 | Offline-First Kiosk | IndexedDB/idb, Workbox, offline status, /sync/answers. | Temporary network loss does not stop core intake. |
| 14 | History, Export, Testing & SIH Demo | Timeline, FHIR-compatible export, pytest/httpx, WebSocket/auth/offline/Gemini failure tests. | Clean end-to-end demonstration is reproducible. |
| 15 | ABHA / ABDM Integration | ABDM sandbox/M2 APIs, abha_links, consent-based FHIR push. | Encounter can be linked and made portable through ABHA. |
| 16 | AYUSH Assessment Module | ayush_questions.json, AYUSH screens, ayush_assessments. | Dashavidha Pariksha and Ahara-Vihara are captured as structured data. |
| 17 | Reminder System | APScheduler/Celery beat, reminder table, SMS/WhatsApp/push gateway. | Medicine and follow-up reminders are scheduled with delivery status. |
| 18 | Smart Follow-up | Prior encounter lookup, prefill/reconfirmation, encounter_links. | Returning patients answer only changed/new questions. |
| 19 | Traceable AI Summary | Per-line provenance in ClinicalSummarySchema and source lookup endpoint. | Each AI summary line can be traced to voice, touch or document evidence. |

# Recommended Dependency-Aware Build Order

Foundation → Auth → Roles → Patient Session → Adaptive Intake → Red Flags → Doctor Dashboard → Real-Time Escalation → OCR → Voice → Gemini → Contradictions → Audit → Offline → History/Export/Tests.

Addendum dependency order from the source plan: AYUSH after Phase 4; Smart Follow-up after Phases 3–4; ABHA/ABDM after Phase 14/FHIR export; Reminder System after Phase 10/approved summary; Traceable AI can be folded into Phase 10 if time allows, otherwise implemented last.

# Phase Gate Principle

Do not move to a downstream AI-dependent phase merely because the UI exists. The upstream workflow must be independently testable first: deterministic intake before Gemini, OCR before Gemini consumes OCR output, and server-side authorization before sensitive dashboard actions.